## Cover
Tender Specifications
Open Procedure
No. ECHA/2013/03
Title: Provision of an HR System, Implementation and Support Services
Annex 5.1.5 – Responsibility Matrix

## RAS
1.0 Project and Maintenance Responsibilities
R = Responsible (the owner of the task) A = Approval (to whom "R" is Accountable and is the authority who approves to sign off on work before it is effective) S = Support (provides resources or plays a supporting role which requires actual work effort)
| 1 | General (during Project and maintenance) | Vendor | ECHA | Comments/remarks
| 1.1 | All necessary components and licenses needed for HR system (the licence and maintenance of licence) | R
| 1.2 | Planning of HR solution project (including integration platform implementation for HR solution) | R | A
| 1.3 | Delivery responsibility of HR solution project | R | S
| 1.4 | Status reporting of HR solution project | R | A
| 1.5 | Quality assurance of HR solution project | R | A
| 1.6 | Organising and control of HR solution project (covers needed customer's resources) | R | A
| 1.7 | Premises and tools of HR solution project (onsite) |  | R
| 1.8 | Premises and tools of HR solution project (offsite) | R
| 1.9 | Required development and user acceptance environments of HR solution project | R | A
| 1.10 | Risk management of HR solution project | R
| 1.11 | Training and initiation of HR solution project staff | R | S
| 1.12 | Ensuring compliance of approval criteria and requirements of ECHA | R | A
| 1.13 | Documentation, help texts, document maintenance, develop guidance of HR solution project | R | A
| 1.14 | Allocation of necessary resources of partner (if applicable) for supporting ECHA (implementation, testing, data migration, deployment, administration support) | R | A
| 1.15 | Provides qualified resources to implementation and maintenance | R | S
| 1.16 | Takes the full responsibility of integrating the HR system to the integration interfaces of ECHA | R | S
| 1.17 | Shared virtual workplaces (to store/ share deliverables of HR solution) | R
| 1.18 | Project management | R | R
| 1.19 | End to end planning and overall responsibility of the project | R | R
| 1.20 | Reviews of the milestones of the project | R | R
| 1.21 | Acceptance of the project |  | R
| 1.22 | Technical and architecture acceptance criteria for final solutions |  | R
| 1.23 | Premises and tools for workshops | S | R
| 1.24 | Status report of the Project | R | S
| 1.25 | Allocation of necessary resources of ECHA for supporting implementation partner (implementation, testing, data migration, deployment, administration support) |  | R
| 1.26 | Hardware, middleware, database, platform and infrastructure | R
| 1.27 | Business requirements | S | R
| 1.28 | Acceptance criteria of business |  | R
Only during maintenance of the HR solution
| 1.29 | Preparation and execution of the annual preventive maintenance plan for HR (production control and support and obligatory changes like upgrades, patches) | R | A
| 1.30 | Preparation of new implementations, changes and modifications to the existing system | R | A
| 1.31 | Setup,configuration, and installation of new implementations, changes and modifications to the existing system | R
| 1.32 | Incident management | R
| 1.33 | Problem management | R
| 2 | Definition (during project and maintenance) | Vendor | ECHA
| 2.1 | Management of functional and technical definitions of HR solution | R | A
| 2.2 | Functional definitions and documentation of HR solution | R | A
| 2.3 | Parameterising of modules and functionality of HR for ECHA | R | A
| 2.4 | Description of integration interfaces of HR solution | R | A
| 2.5 | Integration solution implementation | R | S
| 2.6 | Definitions of the development and user acceptance testing environments | R
| 2.7 | Accepting HR solution functional definitions (for all lines of business, automation needed) |  | R
| 2.8 | Accepting HR solution technical definitions (for all lines of business, automation needed) |  | R
| 2.9 | Functional definitions of the functionality outside HR solution |  | R
| 2.10 | Definitions of hardware platform and definitions of services of platform | R | S
| 2.11 | Business requirements | S | R
| 2.12 | Functional definitions related to HR version changes | R | A
| 2.13 | Technical definitions related to HR version changes | R | A
| 3 | Definition of data migration | Vendor | ECHA
| 3.1 | Data migration process and procedures | R | A
| 3.2 | Definitions of data migration (data structuring and mappings, loadings etc.) | R | A
| 3.3 | Definitions of the data extract from legacy systems | S | R
| 3.4 | Data migration strategy | R | A
| 4 | Implementation (during Project and maintenance) | Vendor | ECHA
| 4.1 | Implementation of HR solution | R
| 4.2 | Implementation of processes of HR and their parameterization | R
| 4.3 | Implementation of integration and parametrization to the ECHA integration interfaces | R | S
| 4.4 | Create development and user acceptance testing environments | R | S
| 4.5 | Installation and set-up of the HR solution in all environments | R | A
| 4.6 | Quality of implementation of HR solution | R | A
| 5 | Implementation of data migration | Vendor | ECHA
| 5.1 | Implementation of data migration (data structuring and mappings, checksums,etc.) | R | A
| 5.2 | Implementation of the data extract from legacy systems | S | R
| 5.3 | Formatting and structuring the data migration data so that it can be loaded to HR | R
| 5.4 | Loading the data migration data to HR | R | A
| 6 | Testing (during Project and maintenance) | Vendor | ECHA
| 6.1 | Unit testing of HR solution in development environment | R
| 6.2 | Integration testing with ECHA environment | S | R
| 6.3 | Unit test cases and test material of HR solution | R | A
| 6.4 | Regression testing, exception testing, resiliency testing, performance testing, security testing and usability testing of HR solution | R | A
| 6.5 | The installation of and migration to acceptance testing environment | R | A
| 6.6 | Repairing of the errors which are found in acceptance before next test deliverable | R | S
| 6.7 | User acceptance testing of HR solution in acceptance test environment |  | R
| 6.8 | Error analysis of user acceptance testing | R | A/S
| 6.9 | User acceptance testing | S | R
| 7 | Testing of data migration | Vendor | ECHA
| 7.1 | Testing the data migration and data loading to HR | R | S
| 7.2 | Data migration test cases | R | A
| 7.3 | Testing of the data extract from legacy systems. |  | R
| 7.4 | Final acceptance of the data migration |  | R
| 8 | Deployment (during Project and maintenance) | Vendor | ECHA
| 8.1 | Technical deployment plan and deployment of HR solution and integration platform | R | S
| 8.2 | Business deployment of HR operations |  | R
| 8.3 | Training of key users | R
| 8.4 | Training of end-users |  | R
| 8.5 | Change management of organisation | S | R
Only during maintenance
| 8.6 | Making of timetables for distributions of new version to production environment | R | A
| 9 | Production Control and Critical Situations | Vendor | ECHA
| 9.1 | Application management and coordination of service providers (hosting facility) | R | S
| 9.2 | User help desk and support (first line) | S | R
| 9.3 | User help desk and support (second and third line) | R | S
| 9.4 | Support to maintenance | R | A
| 9.5 | HR solution running according to requirement levels of Business SLAs | R | A
| 9.6 | Correction of failures and errors caused by HR solution according to requirement levels of SLA | R | A
| 9.7 | Investigation of disturbances in HR solution in co-operation with service providers according to requirements levels of SLA | R | S
| 9.8 | Service level reports of HR solution support, disorders and amount of work needed | R
| 9.9 | Ensure a trouble-free system operation and continuity of development during version changes of HR | R | A
| 9.10 | Ensure a trouble-free system operation when agreed environment changes are made | R
| 9.11 | Production control of HR solution | R | A
| 9.12 | Classification of errors and priorisation of production fixes | S | R
| 9.13 | Scheduling of non-critical error fixes to annual minor development projects. | S | R
| 9.14 | Application monitoring including: monitoring requirements specification; end-to-end application monitoring; monitoring tool ownership & licenses and their management; monitoring tool setup, integration with application customizations; application-specific monitoring tool config & utilisation; monitoring agent setup & configuration; regular monitoring of application activities,; alert/event-monitoring and resolution follow-up; high-availability configuration monitoring; capacity & performance monitoring; application integration monitoring; application security and log-monitoring; regular reporting; backup-monitoring. | R | A
| 9.15 | All IT-operations of the required environments including: backup; restore; HA management (where applicable); adjustment of (performance) tuning parameters; general administration & housekeeping activities. | R | A
| 10 | Change Management | Vendor | ECHA
| 10.1 | Release management | R | A
| 10.2 | License management for applications subject to this service | R
| 10.3 | Licenses for clients/agents of management-SW used by Contractor | R
| 10.4 | Licenses for clients/agents of backup-systems used by Contractor | R
| 10.5 | Installation of software, upgrade & patches | R | A
| 10.6 | Initial installation & setup of the application, verification test | R
| 10.7 | Capacity & Performance Management | R
| 10.8 | Configuration management | R
| 10.9 | Configuration management, HA | R
| 10.10 | Configuration management, connectivity | R
| 10.11 | Code, customisation, schema specification and/or development | R
| 10.12 | Code maintenance (preparation of bug-fixes, patches, upgrades) | R
| 10.13 | integration with other ECHA-related systems | R | R
| 10.14 | Installation of application-upgrades | R | A
| 10.15 | Installation of regular application-patches & service packs | R
| 10.16 | Installation of security-relevant patches and "hot fixes" | R
| 10.17 | Installation of virus-protection software & upgrades | R
| 10.18 | Installation of customisations, where applicable | R
| 10.19 | Installation of systems-management- and backup-agents | R